## Milestones for signoff
# | Activity | # | Milestone | Days | Start | Finish
A1 | Cloud Custodian implementation for Security compliance | M1 | Detailed requirement finalization | 5 | 2020-07-12 | 2020-11-12
|  | M2 | Development and configuration | 20 | 14-12-20 | 2021-08-01
|  | M3 | Implementation / Integration | 12 | 2021-11-01 | 26-01-21
|  | M4 | Documentation and sign off | 5 | 27-01-21 | 2021-02-02
A2 | AMRO Openshift testing and integration | M1 | Requirement gathering | 3 | 2020-09-12 | 2020-11-12
|  | M2 | Detailed requirement finalization | 3 | 2021-07-01 | 2021-11-01
|  | M3 | Design set up | 16 | 2021-12-01 | 2021-02-02
|  | M4 | Implementation and demo | 15 | 2021-03-02 | 23-02-21
A3 | Terraform Enterprise – Productionizing | M1 | Detailed requirement finalization | 9 | 2020-09-12 | 21-12-20
|  | M2 | Development and integration | 20 | 2021-07-01 | 2021-03-02
|  | M3 | Testing and Demo | 10 | 2021-04-02 | 17-02-21
|  | M4 | Documentation and sign off | 1 | 18-02-21 | 18-02-21
A4 | Red Hat Satellite (Integrate with AWS to enable BYOL) | M1 | Detailed requirement finalization | 3 | 2020-09-12 | 2020-11-12
|  | M2 | Solution approach | 10 | 14-12-20 | 25-12-20
|  | M3 | Implementation & configuration | 20 | 18-01-20 | 13-02-20
|  | M4 | Testing and Demo | 5 | 14-02-20 | 20-02-20
A5 | Event Monitoring & Alerting for platform outages and security incidents | M1 | Detailed requirement & sol approach | 12 | 2021-01-02 | 16-02-21
|  | M2 | Development | 12 | 17-02-21 | 2021-04-03
|  | M3 | Implementation / Integration | 5 | 2021-05-03 | 2021-11-03
|  | M4 | Testing and Demo | 5 | 2021-12-03 | 18-03-21
A6 | Service Patterns & Documentation | M1 | Requirement gathering & template | 5 | 2021-01-03 | 2021-05-03
|  | M2 | Documentation | 15 | 2021-08-03 | 26-03-21
A7 | Guidance and recommendation of using AWS Service Catalog vs TFE | M1 | Requirement analysis | 2 | 2021-01-03 | 2021-02-03
|  | M2 | Sample workflow definition | 2 | 2021-03-03 | 2021-04-03
|  | M3 | Comparitive analysis and recommendation | 12 | 2021-05-03 | 22-03-21
|  | M4 | Documentation and sign off | 1 | 23-03-21 | 23-03-21
A8 | Terraform scripts and standardization | M1 | Script development | 20 | 14-12-20 | 2021-08-01
|  | M2 | Testing and Demo | 5 | 2021-11-01 | 15-01-21
|  | M3 | Documentation and sign off | 1 | 18-01-21 | 18-01-21

## A1-Mani
# | High Level activities | Start Date | End Date | Status
A1 | Cloud Custodian implementation for Security compliance
A1.1 | Detailed Requirement gathering and documentation
A1.2 | Feasiblity analysis for the cloud custodian rules and policies |  |  | Working on creating Policies based on AWS best practices.
A1.3 | installation setup | 21-12-2020 | 23-12-2020 | Installation setup has been created on CoreSecurity Account. Waiting for VPC creation to Proceed further.
A1.4 | Prowler Solution Development | 22-12-2020 | 23-12-2020 | Has been done.
A1.5 | Prowler Implementation | 23-12-2020 | 23-12-2020 | Resources are created
A1.6 | Prowler integration with AWS Security HUB | 23-12-2020 |  | Integration has been done
A1.7 | POC of 2 rules and automations |  |  | Done
A1.8 | Implementation planning |  |  | Done
A1.9 | Development of policies |  |  | CIS Level 2 has been implemented
A1.10 | Testing and approval
A1.11 | Implementation |  |  | Implementation done for all the accounts in Organization
A1.12 | Documentation |  |  | Documentation of Prowler also completed
A1.13 | Monitoring

## A2-Jeyashri
A2 | AMRO Openshift testing and integration | Start Date | End Date | Status
A2.1 | Detailed Requirement gathering
A2.2 | Design of the setup
A2.3 | VPC Requirements, isolation, Telemtry access provisioning
A2.4 | Obtaing installation artefacts and installables
A2.5 | Validating installation configurations
A2.6 | Resource provisioning
A2.7 | installation setup
A2.8 | Deployment of cluster
A2.9 | Demo
A2.10 | Documentation and handover

## A3-Jeyashri
A3 | Terraform Enterprise – Productionizing | Start Date | End Date | Status
A3.1 | Detailed Requirement gathering
A3.2 | Feasiblity analysis
A3.3 | Design and solutioning for sentinel integration and setup
A3.4 | Terraform VCS integration analysis
A3.5 | Development of Sentinel policies
A3.6 | Testing & POC Demo
A3.7 | Implementation of Sentinel
A3.8 | Terraform Edirectory integration setup
A3.9 | Terraform Edirectory testing setup
A3.10 | Implementation of VCS integration
A3.11 | Whitepages development support
A3.12 | Documentation

## A4-Prabha
A4 | Red Hat Satellite (Integrate with AWS to enable BYOL) | Start Date | End Date | Status | Comments
A4.1 | Detailed Requirement gathering | 14/12/2020 |  | Inprogress
A4.2 | Design of the setup and Feasiblitiy check with Redhat satellite model | 18/01/2021
A4.3 | Recommendation of the suitable model | 18/01/2021 | 29/01/2021 | Completed | Migrating Unused subscription from onprem to Cloud & Capsule deployment across multiple regions
A4.4 | Network configuration, validation of prerequisites
A4.5 | Installation and configuration
A4.6 | Testing and Demo in Non Prod account
A4.7 | Documentation of the setup | 2021-04-01 |  | Inprogress

## A9
A 9.0 | AWS Systems Manager configuration | Days | Start Date | End Date | Status
A 9.1 | Detailed Requirement gathering | 3 | 2021-02-02 | 2021-02-05
A 9.2 | Design of the setup | 5 | 2021-02-06 | 2021-02-11
A 9.3 | POC of the required services and their inclusion | 5 | 2021-02-12 | 2021-02-17
A 9.4 | AWS SSM agent installation automation | 5 | 2021-02-18 | 2021-02-23
A 9.5 | Testing of automation | 2 | 2021-02-24 | 2021-02-26
A 9.6 | Implementation | 13 | 2021-02-27 | 2021-03-12
A 9.7 | Pipeline workflow design of the reporting queries | 5 | 2021-03-13 | 2021-03-18
A 9.8 | Implementation & Demo | 3 | 2021-03-19 | 2021-03-22
A 9.9 | Documentation of the setup | 3 | 2021-03-23 | 2021-03-26
Formulas:
End Date = [Start Date]+[Days]
Start Date = [End Date, row above]+1

## A8-Sathya
A8 | Terraform scripts and standardization | Days | Start Date | End Date | Status
A8.1 | Detailed Requirement gathering with the resources to be covered | 1
A8.2 | Design standardization and approval | 2
A8.3 | Develop tf for ECS, EKS, Fargate, Lambda, ALB, NLB | 5 | 2021-01-27 |  | In Progress
A8.4 | Develop tf for Elasticsearch, Elasticcache, EMR, RDS (SQLServer, Oracle, MYSQL) | 10 | 2021-01-27 |  | In Progress
A8.5 | Testing of the templates | 5
A8.6 | Demo & Documentation | 2